Time Estimation

|  | Planning | Analysis | Design | Implementation |
| --- | --- | --- | --- | --- |
| Standard percentages | 15% | 20% | 35% | 30% |
| Estimated time based on planning time | Actual: 18 days | 24 days | 42 days | 36 days |

Tasks Identification

| System Request | Name of Task |
| --- | --- |
| 01/10/2026 | Start Date |
| 05/10/2026 | End Date |
| Samer, Abdelfatah | Person assigned to task |
| High | Priority |
| Microsoft Word, GitHub | Resources Needed |
| 5 hours | Estimated Time |
| 4 hours | Actual Time |

| Feasibility Study | Name of Task |
| --- | --- |
| 05/10/2026 | Start Date |
| 12/10/2026 | End Date |
| Yehia, Hussein | Person assigned to task |
| High | Priority |
| Microsoft Word, Excel | Resources Needed |
| 10 hours | Estimated Time |
| 11 hours | Actual Time |

| PERT Chart, Gantt Chart | Name of Task |
| --- | --- |
| 12/10/2026 | Start Date |
| 19/10/2026 | End Date |
| Samer | Person assigned to task |
| High | Priority |
| MS Project | Resources Needed |
| 8 hours | Estimated Time |
| 10 hours | Actual Time |

| Interview (Student Affairs staff) | Name of Task |
| --- | --- |
| 19/10/2026 | Start Date |
| 24/10/2026 | End Date |
| Abdelfatah, Hussein | Person assigned to task |
| Medium | Priority |
| Microsoft Word | Resources Needed |
| 12 hours | Estimated Time |
| 11 hours | Actual Time |

| Questionnaire (employers and graduates) | Name of Task |
| --- | --- |
| 19/10/2026 | Start Date |
| 23/10/2026 | End Date |
| Yehia | Person assigned to task |
| Medium | Priority |
| Google Forms | Resources Needed |
| 6 hours | Estimated Time |
| 6.5 hours | Actual Time |

| Requirements Specification (SRS) | Name of Task |
| --- | --- |
| 24/10/2026 | Start Date |
| 30/10/2026 | End Date |
| Samer, Yehia | Person assigned to task |
| High | Priority |
| Microsoft Word | Resources Needed |
| 2 days | Estimated Time |
| 2 days | Actual Time |

| Use Case Diagram | Name of Task |
| --- | --- |
| 30/10/2026 | Start Date |
| 03/11/2026 | End Date |
| Hussein | Person assigned to task |
| High | Priority |
| StarUML | Resources Needed |
| 1 day 12 hours | Estimated Time |
| 2 days | Actual Time |

| Data Flow Diagram | Name of Task |
| --- | --- |
| 30/10/2026 | Start Date |
| 06/11/2026 | End Date |
| Samer, Abdelfatah | Person assigned to task |
| High | Priority |
| StarUML | Resources Needed |
| 2 days | Estimated Time |
| 3 days | Actual Time |

| Process Specification and Data Store | Name of Task |
| --- | --- |
| 06/11/2026 | Start Date |
| 12/11/2026 | End Date |
| Yehia, Hussein | Person assigned to task |
| High | Priority |
| Microsoft Word | Resources Needed |
| 2 days | Estimated Time |
| 2 days | Actual Time |

| Entity Relationship Diagram | Name of Task |
| --- | --- |
| 12/11/2026 | Start Date |
| 17/11/2026 | End Date |
| Abdelfatah | Person assigned to task |
| High | Priority |
| StarUML | Resources Needed |
| 1 day 12 hours | Estimated Time |
| 1 day | Actual Time |

| Normalization and Database Design | Name of Task |
| --- | --- |
| 17/11/2026 | Start Date |
| 24/11/2026 | End Date |
| Hussein | Person assigned to task |
| High | Priority |
| StarUML | Resources Needed |
| 2 days | Estimated Time |
| 2 days | Actual Time |

| System and Security Design (verification code, QR code, audit log, access control) | Name of Task |
| --- | --- |
| 24/11/2026 | Start Date |
| 03/12/2026 | End Date |
| Samer, Yehia | Person assigned to task |
| High | Priority |
| StarUML, Microsoft Word | Resources Needed |
| 4 days | Estimated Time |
| 3 days | Actual Time |

| User Interface Design (public verification page, admin dashboard) | Name of Task |
| --- | --- |
| 03/12/2026 | Start Date |
| 24/12/2026 | End Date |
| Yehia, Abdelfatah | Person assigned to task |
| Medium | Priority |
| Figma | Resources Needed |
| 10 days | Estimated Time |
| 12 days | Actual Time |

| Admin Dashboard (add, update, revoke certificates) | Name of Task |
| --- | --- |
| 24/12/2026 | Start Date |
| 08/01/2027 | End Date |
| Samer, Hussein | Person assigned to task |
| High | Priority |
| Visual Studio Code | Resources Needed |
| 10 days | Estimated Time |
| 11 days | Actual Time |

| Public Verification Page and QR Code | Name of Task |
| --- | --- |
| 08/01/2027 | Start Date |
| 15/01/2027 | End Date |
| Yehia, Abdelfatah | Person assigned to task |
| High | Priority |
| Visual Studio Code | Resources Needed |
| 5 days | Estimated Time |
| 6 days | Actual Time |

| Audit Log and Security | Name of Task |
| --- | --- |
| 15/01/2027 | Start Date |
| 20/01/2027 | End Date |
| Samer | Person assigned to task |
| High | Priority |
| Visual Studio Code | Resources Needed |
| 4 days | Estimated Time |
| 3 days | Actual Time |

| Student Records Integration and Legacy Data Entry | Name of Task |
| --- | --- |
| 20/01/2027 | Start Date |
| 25/01/2027 | End Date |
| Hussein | Person assigned to task |
| Medium | Priority |
| Excel, Visual Studio Code | Resources Needed |
| 3 days | Estimated Time |
| 3 days | Actual Time |

| Testing, Deployment and Staff Training | Name of Task |
| --- | --- |
| 25/01/2027 | Start Date |
| 29/01/2027 | End Date |
| All team members | Person assigned to task |
| High | Priority |
| Visual Studio Code | Resources Needed |
| 3 days | Estimated Time |
| 3 days | Actual Time |